## Risk Register
Status | ID # | Title | Category | Description | Probability | Impact | Severity | Owner | Response Strategy
Active | 1 | Security vulnerabities | Technical | Weak security that exposes the project and company to cyberthreats like data breaches and ransomware attacks | High (4) | Catastrophic (5) | EXTREME | Chief Security Officer (CSO) | Establish security as a major priority, as project success is impossible without it. Design and enforce security protocols
Active | 2 | Poor architechtural planning | Technical | The architecture of the project was not properly planned out so the project becomes inefficient, prone to failure, and hard to implement | Low (2) | Major (4) | MEDIUM | Project Design Lead | Properly understand the project scope in order to carefully design the architecture of the different systems
Active | 3 | Inter-system integration issues | Technical | The linking of multiple different platforms is challenging and can cause delays or slow work down | Moderate (3) | Moderate (3) | MEDIUM | Technical Project Leader | Design with the intention of system interconnectedness, but keep the components loosely coupled
Active | 4 | Inaccurate timeline estimates | Schedule | The project timeline was built on guesses rather than past data and experiences, so the estimated timeline will be difficult to fulfill due to difference in the planned and actual timelines | Low (2) | Moderate (3) | MEDIUM | Project Mananger (PM) | Gather feedback from the development teams that will be working on the deliverables and incoroporate their estimates into the timeline
Active | 5 | Inadequate delay buffers | Schedule | Not enough time was given inbetween tasks to allow a cushion for delays or undershot timeline estimates | Moderate (3) | Minor (2) | MEDIUM | Project Mananger (PM) | Gather feedback from the development teams that will be working on the deliverables and add buffers at each milestone
Active | 6 | Bottlenecks | Schedule | A workflow that other flows are dependent on the completion of before they can begin is stalled or stopped all together, slowing project progress in more than one area | Moderate (3) | Moderate (3) | MEDIUM | Project Mananger (PM) | Visualize the workflow with a Kanban board (Trello). Identify critical path dependencies. Assign and leverage resource where necessary
Active | 7 | Budget cuts | Financial | Loss of funding for the project | Low (2) | Major (4) | MEDIUM | Project Sponsor | Define project scope to establish a backup plan to move needed funds from the "Nice-to-haves" to the "Must-haves". Draft a MoSCoW-style requirements list
Active | 8 | Poor team communication | People | Teams are unable to properly exchange information in order to complete their work, both within and outside of their teams | Low (2) | Minor (2) | LOW | Project Mananger (PM) | Have a universal communication method. Establish efficient documentation protocols
Active | 9 | Team members skill gaps | People | Team members do not possess the necessary skills to complete their tasks, so work quality is not adequate and the timeline is delayed | Low (2) | Minor (2) | LOW | Project Mananger (PM) | Have team leads assign roles and tasks based on team members' specialized skills. Pair junior members with senior mentors
Active | 10 | Inadequate stakeholder engagement | People | Stakeholders are not fully engaged, so decisions regarding the course of the project | Moderate (3) | Moderate (3) | MEDIUM | Project Mananger (PM) | Record weekly stakeholder update videos. Listen to feedback and take action based off it