## Risk Register
Status | ID # | Title | Category | Description | Probability | Impact | Severity | Owner | Response Strategy
Active | 1 | Security vulnerabities | Technical | Weak security that exposes the project and company to cyberthreats like data breaches and ransomware attacks | High (4) | Catastrophic (5) | EXTREME | Chief Security Officer (CSO) | Establish security as a major priority, as project success is impossible without it. Design and enforce security protocols
Active | 2 | Poor architechtural planning | Technical | The architecture of the project was not properly planned out so the project becomes inefficient, prone to failure, and hard to implement | Low (2) | Major (4) | MEDIUM | Project Design Lead | Properly understand the project scope in order to carefully design the architecture of the different systems
Active | 3 | Inter-system integration issues | Technical | The linking of multiple different platforms is challenging and can cause delays or slow work down | Moderate (3) | Moderate (3) | MEDIUM | Technical Project Leader | Design with the intention of system interconnectedness, but keep the components loosely coupled
Active | 4 | Inaccurate timeline estimates | Schedule | The project timeline was built on guesses rather than past data and experiences, so the estimated timeline will be difficult to fulfill due to difference in the planned and actual timelines | Low (2) | Moderate (3) | MEDIUM | Project Mananger (PM) | Gather feedback from the development teams that will be working on the deliverables and incoroporate their estimates into the timeline
Active | 5 | Inadequate delay buffers | Schedule | Not enough time was given inbetween tasks to allow a cushion for delays or undershot timeline estimates | Moderate (3) | Minor (2) | MEDIUM | Project Mananger (PM) | Gather feedback from the development teams that will be working on the deliverables and add buffers at each milestone
Active | 6 | Bottlenecks | Schedule | A workflow that other flows are dependent on the completion of before they can begin is stalled or stopped all together, slowing project progress in more than one area | Moderate (3) | Moderate (3) | MEDIUM | Project Mananger (PM) | Visualize the workflow with a Kanban board (Trello). Identify critical path dependencies. Assign and leverage resource where necessary
Active | 7 | Budget cuts | Financial | Loss of funding for the project | Low (2) | Major (4) | MEDIUM | Project Sponsor | Define project scope to establish a backup plan to move needed funds from the "Nice-to-haves" to the "Must-haves". Draft a MoSCoW-style requirements list
Active | 8 | Poor team communication | People | Teams are unable to properly exchange information in order to complete their work, both within and outside of their teams | Low (2) | Minor (2) | LOW | Project Mananger (PM) | Have a universal communication method. Establish efficient documentation protocols
Active | 9 | Team members skill gaps | People | Team members do not possess the necessary skills to complete their tasks, so work quality is not adequate and the timeline is delayed | Low (2) | Minor (2) | LOW | Project Mananger (PM) | Have team leads assign roles and tasks based on team members' specialized skills. Pair junior members with senior mentors
Active | 10 | Inadequate stakeholder engagement | People | Stakeholders are not fully engaged, so decisions regarding the course of the project | Moderate (3) | Moderate (3) | MEDIUM | Project Mananger (PM) | Record weekly stakeholder update videos. Listen to feedback and take action based off it

## Roles and Resources
Roles | Name | FTE % | Estimated Hours | Hourly Rate | Cost
Project Manager | Tony | 0.5 | 240 | 100 | 24000
Lead System Archeitect | Casey | 1 | 480 | 180 | 86400 | Management and Architecture Subtotal: | 110400
Lead Mobile Developer | Kevin | 1 | 480 | 150 | 72000
Senior Mobile Developer | Tyler | 1 | 480 | 110 | 52800
Senior Mobile Developer | Amy | 1 | 480 | 110 | 52800
Mobile Developer | Sophia | 1 | 480 | 80 | 38400
Mobile Developer | Hui | 1 | 480 | 80 | 38400 | Mobile Team Subtotal: | 254400
Lead Web Developer | Nico | 1 | 480 | 140 | 67200
Senior Frontend Developer | Irianna | 1 | 480 | 115 | 55200
Senior UI/UX Lead | Evelyn | 1 | 480 | 115 | 55200
Frontend Developer | Tyrone | 1 | 480 | 85 | 40800
UI/UX Developer | Mikaela | 1 | 480 | 85 | 40800 | Web Team Subtotal: | 259200
Full-Stack Developer (Flexible Assignment) | Jeffrey | 1 | 480 | 130 | 62400 | Full-Stack Subtotal: | 62400
Backend Lead Developer | Sophie | 1 | 480 | 150 | 72000
Senior Backend Developer | Lando | 1 | 480 | 120 | 57600
Backend Developer | Franklin | 1 | 480 | 90 | 43200
Database Administrator | Leon | 1 | 480 | 125 | 60000
Cloud Infrastructure Engineer | Taylor | 1 | 480 | 150 | 72000 | Backend Team Subtotal: | 304800
Geographic Information System Integration Lead | Kim | 1 | 480 | 145 | 69600
Geographic Information System Analyst | Cody | 1 | 480 | 100 | 48000
Geographic Information System Technician | Carlos | 1 | 480 | 70 | 33600
Spatial Data Engineer | Luca | 1 | 480 | 130 | 62400
Cartographer | Sergei | 1 | 480 | 80 | 38400 | Mapping and Location Services Team Subtotal: | 252000
Head of Payments (Payments Team Lead) | Caitlyn | 1 | 480 | 185 | 88800
Payments Security Engineer | Violet | 1 | 480 | 170 | 81600
Payments Intergration Engineer | Jose | 1 | 480 | 85 | 40800
Payments Operations Specialist | Nathan | 1 | 480 | 85 | 40800
Fraud and Risk Manager | Marcus | 1 | 480 | 160 | 76800 | Payment Team Subtotal: | 328800
QA Lead | Nicole | 1 | 480 | 110 | 52800
QA Test Manager | Thomas | 1 | 480 | 120 | 57600
QA Engineer | Benny | 1 | 480 | 80 | 38400
QA Test Analyst | Silvio | 1 | 480 | 75 | 36000
QA Tester | Franchesca | 1 | 480 | 55 | 26400
QA Tester | Colin | 1 | 480 | 55 | 26400 | QA and Testing Team Subtotal: | 237600
Total |  |  |  |  | 1809600 |  | 1809600

## Resource and Cost Plan
Item | Category | Quantity/Months | Unit Cost | Duration (Months) | Total | Notes
Management and Architecture Pay | Labor | 240 | 460 | 3 | 110400
Mobile Application Team Pay | Labor | 600 | 424 | 3 | 254400
Web Application Team Pay | Labor | 600 | 432 | 3 | 259200
Fullstack Team Pay | Labor | 160 | 390 | 3 | 62400
Backend/API Team Pay | Labor | 600 | 508 | 3 | 304800
Mapping & Location Services Team Pay | Labor | 600 | 420 | 3 | 252000
Payment Integration Team | Labor | 600 | 548 | 3 | 328800
Quality Assurance & and Testing Team | Labor | 720 | 330 | 3 | 237600
Cloud Hosting | Infrastructure | 2000 | 2000 | 3 | 6000
Licenses | Tools | 20000 | 20000 | 3 | 60000
Third-Party APIs | Tools | 8000 | 8000 | 3 | 24000
Contingency | Reserver | 10% | Applied to Total | N/A | 2089560

## RACI Matrix
Task/Role | PM | Architect | Mobile Team | Web Team | Full-Stack | Backend | Mapping and Location Services | Payment | QA and Testing
System Architecture Design | A | R | C | C | C | C | C | C | I
Cloud Hosting & Infrastructure Setup | I | A | C | I | I | R | C | C | I
UI/UX Design Wireframes | A | C | I | C | R | R | I | I | I
Mobile App Implementation | A | C | I | R | C | C | I | I | I
Web Frontend Implementation | A | C | I | C | R | R | I | I | I
Backend Service & API Development | A | C | I | C | R | R | I | I | I
GIS Mapping Integration | A | C | I | C | C | C | R | I | I
Payment Gateway Integration | A | C | C | C | C | C | I | R | I
Fraud & Risk Rules Definition | I | C | A | I | R | R | I | C | I
End-to-End QA Testing Cycles | A | I | I | C | C | C | C | C | R